## Week 1
Project Name: | StyleSync
Group Number: | 11
Course: | ACIT 2911
Person | Question | Week 01 |  | 2024-04-29
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Angad Bains | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: Identify which parking lots around my area that has spots avaliable Solution: Parking Lot Availability Tracker Review Project Notes and Announcements Familarize GitHub Commands
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Work on Team Charter
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there
Tanish Bansal | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Review Project Notes and Announcements Familarize GitHub Commands
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Work on Team Charter
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there
Matthew Chow | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: Sound mixing programs are expensive and requires training, we want to have a simple sound file merger Solution: Online App to import 2 audio files and merge them
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Design the User Interface
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there
Chae Won (Matilda) Kim | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: There is a lot of waste in Fast Fashion and closets being too full of things Solution: Personal Fashion Tracking App, takes in closet item Familarize GitHub Commands Review Project Notes and Announcements
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | GIVEN ROLE: PRODUCT OWNER FOR WEEK 1 In-Class Meeting: Quiz #1 - Agile Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) Identify functionality of the application Typing the Team Charter
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there
Charley Liao | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: File management and sorting files can be cumbersome and time consuming Solution: Web Application or Executable programs that will take in a directory, allow user to indicate how to manage the files, and create folders for sorting Review Project Notes and Annoucements Familarize GitHub Commands
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | GIVEN ROLE: SCRUM MASTER FOR WEEK 1 - Organize Trello In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Type out and work on Status Report - Work on Team Charter - Typing and work onStandup Meeting Notes
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there - As Scrum Master, it was difficult keeping overthinking - Using a MacOS Computer with M2 Chip, may cause issues when reading files from WindowsOS
Misha Makaroff | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: Tracking Food Intake and Nutrition has a Static database and does not have a daily dashboard / summary Solution: Nutrition application that allows us to input our food intake with unit of measurement and application will show a dashboard of daily intake Review Project Notes and Announcements Familarize GitHub Commands
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Design the User Interface - Work on Team Charter - Work on User Stories
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there

## Week 2
Project Name: | StyleSync
Group Number: | 11
Course: | ACIT 2911
Person | Question | Week 02 |  | <Date>
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Angad Bains | What did you do yesterday? | N/A
| What will you work on today? | Initial Course for ACIT 2911
| Do you have any obstacles? | N/A
Tanish Bansal | What did you do yesterday? | N/A
| What will you work on today? | Initial Course for ACIT 2911
| Do you have any obstacles? | N/A
Matthew Chow | What did you do yesterday? | N/A
| What will you work on today? | Initial Course for ACIT 2911
| Do you have any obstacles? | N/A
Chae Won (Matilda) Kim | What did you do yesterday? | N/A
| What will you work on today? | Initial Course for ACIT 2911
| Do you have any obstacles? | N/A
Charley Liao | What did you do yesterday? | N/A
| What will you work on today? | Initial Course for ACIT 2911
| Do you have any obstacles? | N/A
Misha Makaroff | What did you do yesterday? | N/A
| What will you work on today? | Initial Course for ACIT 2911
| Do you have any obstacles? | N/A