## Week 1
Project Name: | StyleSync
Group Number: | 11
Course: | ACIT 2911
Person | Question | Week 01 |  | 2024-04-29
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Angad Bains | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: Identify which parking lots around my area that has spots avaliable Solution: Parking Lot Availability Tracker Review Project Notes and Announcements Familarize GitHub Commands | Finish Functionalities Possible Category filters for app | Administration Work: - Completion of Peer Evaluation - Reviewed and Added info to Project Proposal Draft Researched Tools used for this project - SQLite - Python
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Work on Team Charter | Admistrative work Assist Presentation | Group Presentation
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there | N/A | N/A
Tanish Bansal | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Review Project Notes and Announcements Familarize GitHub Commands | Work on basic Layout of Code Discuss text stats - Utilizing Python for App File Structure Layout Back-end Look into Flask, SQLite, SQLalchemy Middle-Ware Flask Login Front-end HTML Bootstrap | Continued Working on Prelim Code: - Log-in Page - Register Page ** Note It is in prep for Sprint #1, trying out different tools Administration: - Peer Evaluation
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Work on Team Charter | Working on Industry and Professional Layout of File structure Basic Functionality Look into (Home Page) Have the server up and running Basic Layout or vision | Group Presentation
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there | Choosing the front-end framework Looking for things that are useful for the team Determinine which language would best fit the sitaution and researching | Sleep Depreviation
Matthew Chow | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: Sound mixing programs are expensive and requires training, we want to have a simple sound file merger Solution: Online App to import 2 audio files and merge them | Discuss functionalities of APP Simple WIP design of front end alongside Misha General Rough Draft | Administration: - Completition Peer Evaluation - Review Presentation Project: - UI Figma Basic Layout
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Design the User Interface | Administrative Work (Peer Evaluation) Power Point, continue working on layout -> BrainStorming | Group Presentation
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there | Layout Designs that may conflict with opinions and design layout Slightly off to desired outcomes (Thinking Ahead) | Sleep Depreviation
Chae Won (Matilda) Kim | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: There is a lot of waste in Fast Fashion and closets being too full of things Solution: Personal Fashion Tracking App, takes in closet item Familarize GitHub Commands Review Project Notes and Announcements | Administrative work - Team Charter - Proposal Draft | Administration: - Completition of Peer Evaluation - Completition of PPT Presentation
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | GIVEN ROLE: PRODUCT OWNER FOR WEEK 1 In-Class Meeting: Quiz #1 - Agile Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) Identify functionality of the application Typing the Team Charter | Power Point - Adding Content to Slides - Share with everyone so people can put inputs Administration - Peer Evaluation | Group Presentation
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there | Filling out Proposal, could not finish everything - Did not decide what program we are going to use - What approaches we are going to do for the project - Loud Room | Currently Moving Residency
Charley Liao | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: File management and sorting files can be cumbersome and time consuming Solution: Web Application or Executable programs that will take in a directory, allow user to indicate how to manage the files, and create folders for sorting Review Project Notes and Annoucements Familarize GitHub Commands | Administration Work: - Reviewing the Team Charter - Reviewing the Project Proposal, adding the information required for deliverables Establishing the Notes for the Week 1 Deliverable Presentation | Administration Work: - Completiton of Week 1 Status Report - Completition of Peer Evaluation - Worked on Project Proposal Draft Project: - Review PPT Deliverables to ensure knowledge of project
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | GIVEN ROLE: SCRUM MASTER FOR WEEK 1 - Organize Trello In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Type out and work on Status Report - Work on Team Charter - Typing and work onStandup Meeting Notes | Completition of Administration Package: - Notes for PowerPoint (Adding Contents to Slide) - Peer Evaluation - Type out Stand-up Meeting Template - Week 01 Status Report | Group Presentation Administration Work: - Team Charter Completion - Project Proposal Completion
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there - As Scrum Master, it was difficult keeping overthinking - Using a MacOS Computer with M2 Chip, may cause issues when reading files from WindowsOS | Filling out Proposal, could not finish everything - Did not decide what program we are going to use - What approaches we are going to do for the project - Loud | Thursday Evening Work Shift till 10 pm Lack of sleep, 4 hours of sleep (Sleep Deprivation)
Misha Makaroff | What did you do yesterday? | N/A | Review Project Scope for ACIT 2911 | Come up with one idea Problem: Tracking Food Intake and Nutrition has a Static database and does not have a daily dashboard / summary Solution: Nutrition application that allows us to input our food intake with unit of measurement and application will show a dashboard of daily intake Review Project Notes and Announcements Familarize GitHub Commands | Brainstorming UI Stuff - Mock-up wsing Figma of front end (Quick Sketch) User Stories, added ideas to trello | Administration Work: - Completition of Peer Evaluation – Worked PPTX Project: - Looked into how to set up a Login Page UI
| What will you work on today? | Initial Course for ACIT 2911 | Initial Kick-off Meeting with Group Members | In-Class Meeting: - Quiz #1 - Agile - Vote on which topic/idea (problem and solution) to work on - Fashion App (StyleSync) - Identify functionality of the application - Design the User Interface - Work on Team Charter - Work on User Stories | Administrative: - Peer Evaluation - Login-Page Design (possibilities) UI, working alongside Matt | Group Presentation
| Do you have any obstacles? | N/A | N/A | In-Class Meeting: - Noisy Room - Learning Curve, working together for the first time - New to Agile Mindset, Making Small Mistakes here and there | Lack of Experience, causing potential feature creep | Course Work, and lack of coffee

## Week 2
Project Name: | StyleSync
Group Number: | 11
Course: | ACIT 2911
Person | Question | Week 02 |  | 2024-05-06
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Angad Bains | What did you do yesterday? | Database work | Database Design+D6:D22D9DD6:D23 | Figured out to make tags and implement
| What will you work on today? | More database work | Database Design and | Improved ERD, added sub catergories
| Do you have any obstacles? | Pokemon, learning new tools | Git problems | Difficult to find database structure and uncertainy
Tanish Bansal | What did you do yesterday? | N/A | API Branching Database | Set up branches and work flow. Database design
| What will you work on today? | N/A | Branching Login/Regristration database | New database design?
| Do you have any obstacles? | N/A | Understanding Git and making branches | Git is hard and change issues. Database issues, deliveries
Matthew Chow | What did you do yesterday? | Created test routes Created homepage.html Split Homepage and Home | Designed New outfit page | Did not work much on project
| What will you work on today? | Keep working on wardrobe.html More html and push | Work with Misha to continue designing webpages for homepage, new outfits, and wardrobe | Routes, HTML, CSS with Misha, Branching
| Do you have any obstacles? | Doing course work repo problem | Git problems and pushing | Git problem
Chae Won (Matilda) Kim | What did you do yesterday? | Login page regristration page | Design regristration page | Discuss branch issues, Admin work
| What will you work on today? | Finding logos Admin work front end design for login and regristration page | Admin work such as the Powerpoint | Found images for html pages
| Do you have any obstacles? | Learning new tools settling in new home | Learning how git works and api routes | Merging login page, regristration page
Charley Liao | What did you do yesterday? | Reviewing case studies class diagram, creating test case | Continued working on database with Angad, fixed the ERD | Understand branching and database, to build test case scenario. Writing notes on ppt
| What will you work on today? | Test cases admin work assisting version control | Admin work and building the database | Database with Angad to streamline. Relationships
| Do you have any obstacles? | Sunday is disconnect day | Merge conflicts and version control | Syncing up with Git. Database issues. Need more screens
Misha Makaroff | What did you do yesterday? | did homepage.html | Research on the weather API Research on git | Learning github, GPS location for weather
| What will you work on today? | API for weather and location for implemenation | Continue working on the design on html pages | Did routes, css, html with Matthew
| Do you have any obstacles? | Nothing | Git problems | Lots of merging and bringing, and GIT problems. Getting ready for Friday presentation.

## Week 3
Project Name: | StyleSync
Group Number: | 11
Course: | ACIT 2911
Person | Question | Week 02 |  | 2024-05-13
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Angad Bains | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Tanish Bansal | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Matthew Chow | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Chae Won (Matilda) Kim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Charley Liao | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Misha Makaroff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 4
Project Name: | StyleSync
Group Number: | 11
Course: | ACIT 2911
Person | Question | Week 02 |  | 2024-05-20
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Angad Bains | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Tanish Bansal | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Matthew Chow | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Chae Won (Matilda) Kim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Charley Liao | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Misha Makaroff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?